## Sheet1
date reported | who reported it | defect | date fixed | who fixed it | how it was fixed
2020-11-05 | Tristan Gant | Bishop attack function not working | 2020-11-08 | Fengming Yang | fixed reaching end of function without returning anything
2020-11-05 | Tristan Gant | Segfault on checkmate | 2020-11-07 | Tristan Gant | Reworked how the checkmate function called checkmate
2020-11-05 | Tristan Gant | Pawns able to move backwards | 2020-11-05 | Tristan Gant | When a pawn moves the current player needs to be checked so it moves the right way
2020-11-06 | Tristan Gant | Checkmate happens early even when piece can be attacked | 2020-11-08 | Tristan Gant | Check if the piece that can attack the king can be attacked
2020-11-07 | Tristan Gant | Player 2 king is not in the correct position | 2020-11-07 | Tristan Gant | Moved king over one space
2020-11-08 | Tristan Gant | Queen move and attack function not working | 2020-11-08 | Chenyu Hao | Queen move and attack function implemented